Federal Democratic Republic of Ethiopia

Ministry of Urban and Infrastructure, Ministry of Labor and Skills, Ministry of Women and Social Affairs.

Urban Productive Safety Net and Jobs Project [P169943]

Third Additional Financing

ENVIRONMENTAL and SOCIAL

COMMITMENT PLAN (ESCP)

[Appraisal]

ENVIRONMENTAL AND SOCIAL COMMITMENT PLAN

- The Federal Democratic Republic of Ethiopia (Recipient) is implementing the Urban Productive Safety Net and Jobs Project (P169943) (the Project),-which is the Original Financing in the form of a grant ((D732-ET), including as financed under the first Additional Financing – Urban Productive Safety Net and Jobs Project (P177654) with MDTF-FD Grant (TF0B8764) and  UPSNP-MDTF Grant (TF0B8808) Second Additional Financing - Urban Safety Net and Jobs Project (P181550)-IDA credit (E301-ET). The Recipient will implement the scale up of the Project under the third Additional Financing with the involvement of the Ministry of Urban and Infrastructure, the Ministry of Labor and Skills (MoLS) and the Ministry of Women and Social Affairs (MoWSA), as set out in the financing agreement between the Recipient and the International Development Association (the Association) (the Financing Agreement) for the third Additional Financing. The Association  has agreed to provide (a) the original financing (P169943), (b) first additional financing (P177654), (c) second additional financing (P181550) and (d) third additional financing, as set out in the related financing and grant Agreements. This Environmental and Social Commitment Plan (ESCP) supersedes previous versions of the ESCP for the Project and shall apply both to the original and the additional financings for the Project referred to above.

- The Recipient shall ensure that the Project is carried out in accordance with the Environmental and Social Standards (ESSs) and this ESCP, in a manner acceptable to the Association. The ESCP is a part of the Financing Agreement. Unless otherwise defined in this ESCP, capitalized terms used in this ESCP have the meanings ascribed to them in the Financing Agreement.

- Without limitation to the foregoing, this ESCP sets out material measures and actions that the Recipient shall carry out or cause to be carried out, including, as applicable, their respective timeframes; institutional, staffing, training, monitoring and reporting arrangements; and grievance management. The ESCP also sets out the environmental and social (E&S) documents that shall be prepared or updated, consulted, disclosed and implemented under the Project, consistent with the ESSs, in form and substance acceptable to the Association. Once adopted, said E&S documents may be revised from time to time with prior written agreement by the Association. As provided for under the referred Financing Agreement, the Recipient shall ensure that there are sufficient funds available to cover the costs of implementing the ESCP.

- As agreed by the Association and the Recipient, this ESCP will be revised from time to time, if necessary, to reflect adaptive management of Project changes or unforeseen circumstances or in response to Project performance. In such circumstances, the Association and the Recipient through the Ministry of Urban and Infrastructure agree to update the ESCP to reflect these changes through an exchange of letters signed between the Association and the Minster, Ministry of Urban and Infrastructure. The Recipient shall promptly disclose the updated ESCP.

- The subsection on “Indicators for Implementation Readiness” below identifies the actions and measures to be monitored to assess Project readiness to begin implementation in accordance with this ESCP. Nevertheless, all actions and measures in this ESCP shall be implemented as set out in the “Timeframe” column below irrespective of whether they are listed in the referred subsection.

| MATERIAL MEASURES AND ACTIONS |  | TIMEFRAME | RESPONSIBLE ENTITY |
| --- | --- | --- | --- |
| IMPLEMENTATION ARRANGEMENTS AND CAPACITY SUPPORT |  |  |  |
| A | ORGANIZATIONAL STRUCTURE a. Maintain the Federal Project Coordination Unit (FPCU) with qualified staff and adequate resources to support the management of environmental, social, health, and safety (ESHS risks and impacts of the Project. This includes a social specialist, an environmental specialist, a citizen engagement specialist, and a gender specialist, all deployed at the federal level. These specialists will be tasked with ESHS management under the FPCU and must be qualified, full-time staff. b. Each Project beneficiary town/city shall maintain a functional environmental and social risk management organizational structure with one E&S safeguard focal person. Each Regional level project implementation unit shall recruit and maintain one E&S safeguards specialist, responsible for ensuring full compliance with the ESSs and relevant instruments. Some cities (Regional and zonal capitals) need more than one E&S person to ensure the proportionality of the risks. Each of the Regional and City Administration Bureau of Women and Social Affairs (BoWSA) offices shall maintain one social worker. c. The Ministry of Women and Social Affairs (MoWSA) shall recruit and maintain one social specialist. | a. Maintain the ESHS organizational structure at FPCU throughout Project implementation. b. Maintain regional E&S safeguards specialists throughout Project implementation. Assign and maintain the city E&S safeguard focal persons throughout Project implementation. c. Recruit the social specialist at MoWSA prior to commencing activities under Part 3 of third Additional Financing, and thereafter maintain throughout Project implementation. | Ministry of Urban and Infrastructure/ FPCU MoWSA, Regions, city administrations, and beneficiary towns/cities. |
| B | CAPACITY BUILDING PLAN/MEASURES Training to be provided for FPCU staff, regional and city level experts, officials and stakeholders on: - - Environmental and Social Management Framework (ESMF) of the Project - Occupational health and safety risk management - Waste management practices in line with ESS3, World Bank Group Environmental, Health, and Safety (EHS) Guidelines, and Good International Industry Practices (GIIP) - Preparation and implementation of site-specific environmental and social risk management instruments (Environmental and Social Management Plans (ESMPs) and Resettlement Action Plans (RAPs)) - Stakeholder mapping and engagement, and grievance mechanisms - specific aspects of environmental and social assessment - Sexual exploitation and abuse/sexual harassment (SEA/SH) and gender based violence (GBV) risks, and SEA/SH management measures - Emergency preparedness and response - Public work codes of conduct and community health and safety. Training for Project beneficiaries on occupational health and safety and GBV-SEA/SH, including on emergency prevention and preparedness and response arrangements to emergency situations, as well as on the use of the project’s grievance mechanisms. | Throughout Project implementation Project workers trained on all areas relevant to them, including GBV, immediately upon hiring and before Project workers engage in work. | The Ministry of Urban and Infrastructure, /FPCU; MoWSA, MoLS participating Regions and towns/cities |
| MONITORING AND REPORTING |  |  |  |
| C | REGULAR REPORTING Prepare and submit to the Association regular monitoring reports on the ESHS performance of the Project, including but not limited to the implementation of the ESCP, status of preparation and implementation of E&S instruments required under the ESCP, stakeholder engagement activities, and functioning of the grievance mechanisms. Information about Project-related grievances received through the different participating agencies and the overall E&S management performance of the Project will be consolidated and included in the regular reports prepared by the FPCU. | Submit quarterly and annual reports throughout Project implementation period to the Association no later than fifteen (15) days after the end of each reporting period. | Ministry of Urban and Infrastructure/FPCU, MoLS and MoWSA. |
| D | CONTRACTORS’ MONTHLY REPORTS Require contractors and supervising firms to provide monthly monitoring reports on E&S performance in accordance with the metrics specified in the respective bidding documents and contracts and submit such reports to the Association. | Submit the monthly reports to the Association upon request or as annexes to the reports to be submitted under action C above. | Ministry of Urban and Infrastructure/FPCU, Regions, town/city administrations. |
| E | INCIDENTS AND ACCIDENTS The FPCU shall be responsible for promptly notifying the Association of any incident or accident related to the Project which has, or is likely to have, a significant adverse effect on the environment, the affected communities, the public or workers, including, inter alia, cases of SEA/SH, , and accidents that result in death, serious or multiple injury that may result in disability. Provide sufficient detail regarding the scope, severity, and possible causes of the incident or accident, indicating immediate measures taken or that are planned to be taken to address it, and any information provided by any contractor and/or supervising firm, as appropriate. Provide available details of the incident or accident to the Association upon request. Arrange for an appropriate review of the incident or accident to establish its immediate, underlying and root causes. Prepare, agree with the Association, and implement a Corrective Action Plan that sets out the measures and actions to be taken to address the incident or accident and prevent its recurrence. | Notify the Association no later than forty-eight (48) hours after learning of the incident or accident. Provide available details upon request. Provide review report and Corrective Action Plan to the Association no later than ten (10) days following the submission of the initial notice, unless a different timeframe is agreed to in writing by the Association. | Ministry of Urban and Infrastructure/FPCU, MoLs and MoWSA. |
| ESS 1: ASSESSMENT AND MANAGEMENT OF ENVIRONMENTAL AND SOCIAL RISKS AND IMPACTS |  |  |  |
| 1.1 | ENVIRONMENTAL AND SOCIAL ASSESSMENTS AND/OR PLANS Update and implement the environmental and social risk management instruments prepared for the parent Project, namely, the ESMF, Resettlement Policy Framework (RPF), Social Risk Assessment, GBV Risk Assessment and Action Plan, Stakeholder Engagement Plan (SEP), and Labor Management Procedures (LMP) to identify and assess the environmental and social risks and impacts of the Project and provide for appropriate mitigation measures in a manner acceptable to the Association and consistent with the Association’s ESF. In terms of site-specific subprojects: 1. Prepare and implement ESMPs for public work or other relevant subprojects and Project activities. 2. Regional and city project implementing entities should also adopt and implement the subproject site-specific ESMPs as set out in the updated ESMF. The proposed subprojects and Project activities described in the exclusion list set out in the updated ESMF shall be ineligible to receive financing under the Project. | Instruments prepared for the parent Project shall be updated and implemented throughout Project implementation. In terms of site-specific sub projects: - 1. Prepare ESMP prior to the commencement of public work activities and thereafter implement the ESMP throughout Project implementation. 2. Adopt the ESMP before launching the bidding process for the respective subproject prior to the carrying out of construction works that requires the adoption of such ESMP. Once adopted, implement the respective ESMP throughout Project implementation. | Ministry of Urban and Infrastructure/FPCU, MoLS and MoWSA. |
| 1.2 | MANAGEMENT OF CONTRACTORS Incorporate the relevant aspects of the ESCP, including, inter alia, the relevant E&S instruments, the LMP, and public works code of conduct, into the ESHS specifications of the procurement documents and contracts with contractors and supervising firms. Thereafter ensure that the contractors and supervising firms comply and cause subcontractors to comply with the ESHS specifications of their respective contracts. | As part of the preparation of procurement documents and respective contracts. Supervise contractors throughout Project implementation. Copies of relevant contracts provided to the Association upon request. | Ministry of Urban and Infrastructure/FPCU |
| 1.3 | TECHNICAL ASSISTANCE Ensure that the consultancies, studies, and any other technical assistance activities under the Project are carried out in accordance with terms of reference acceptable to the Association, that are consistent with the ESSs. Thereafter ensure that the outputs of such activities comply with the terms of reference. | Throughout Project implementation. | Ministry of Urban and Infrastructure/ FPCU, MoLS and MOWSA |
| 1.4 | CONTINGENT EMERGENCY RESPONSE FINANCING Adopt any E&S instruments which may be required for activities under a CERC component of the Project, in accordance with a CERC Manual and, if applicable, CERC-ESMF or CERC-ESMF Addendum and the ESSs, and thereafter implement the measures and actions required under E&S instruments, within the timeframes specified in the E&S instruments throughout Project implementation. Should the CERC component be activated: - Include in the CERC Emergency Action Plan a description and assessment of the environmental and social characteristics, risks and impacts of the proposed activities, consistent with the CERC-ESMF. - Prepare and disclose the respective environmental and social management measures and implement any updates to the Project ESMF and CERC-ESMF and other relevant E&S plans/instruments, as agreed with the Association Implement the CERC E&S measures. | Prior to approval of the CERC Emergency Action Plan Adopt any required E&S instrument and include it as part of the respective bidding process, if applicable, and in any case, before the carrying out of the relevant Project activities for which the E&S instrument is required. Implement the E&S instruments in accordance with their terms, throughout Project implementation. Prepare, consult upon and disclose the CERC ESMF, if the CERC activities do require new environmental and social assessments. | National Disaster Risk Management Commission, Ministry of Finance, Ministry of Urban and Infrastructure, Refugees and Returnees Service (RRS) |
| ESS 2: LABOR AND WORKING CONDITIONS |  |  |  |
| 2.1 | LABOR MANAGEMENT PROCEDURES Update and implement the LMP that has been developed for the Project. | The updated LMP of the parent Project shall apply to the activities being implemented under the third Additional Financing and shall be implemented throughout Project implementation. | Ministry of Urban and Infrastructure/FPCU, MoLS and MoWSA |
| 2.2 | OCCUPATIONAL HEALTH AND SAFETY MANAGEMENT PLAN OR MEASURES Prepare and implement OHS Management Plan or measures as part of ESMPs prepared under action 1.1 above and proportionate to the risk, to assess and manage the OHS risks and impacts of the Project. Require contractors and subcontractors to prepare and implement OHS Management Measures or Plan in accordance with the Environmental and Social Management Plan. | Same timeframe as for preparation of ESMPs under action 1.1 above, and implement throughout Project implementation. | Ministry of Urban and Infrastructure/FPCU, MoLs and MoWSA. |
| 2.3 | GRIEVANCE MECHANISM FOR PROJECT WORKERS Maintain, and operate a functional grievance redress mechanism (GRM) for Project beneficiaries consistent with ESS2 as described in the LMP. Implement and document, and cause participating cities to implement and document, workers’ GRM throughout Project implementation and regularly report on its results. | The GRM established for the Project shall be maintained throughout Project implementation. | Ministry of Urban and Infrastructure/FPCU, MoLs, MoWSA, RRS, Regions and participating cities. |
| ESS 3: RESOURCE EFFICIENCY AND POLLUTION PREVENTION AND MANAGEMENT |  |  |  |
| 3.1 | WASTE MANAGEMENT MEASURES Incorporate waste management measures, as part of the ESMPs prepared for the Project under action 1.1 above, to manage hazardous and non-hazardous wastes, consistent with ESS3. | Prepare ESMPs with the waste management measures before the commencement of public work activities and thereafter implement it throughout Project implementation. | Ministry of Urban and Infrastructure/FPCU, Regions and participating cities. |
| 3.2 | RESOURCE EFFICIENCY AND POLLUTION PREVENTION AND MANAGEMENT Incorporate resource efficiency and pollution prevention and management measures in the ESMPs to be prepared under action 1.1 above. The site-specific environmental and social risk management tools such as ESMPs (which will be prepared based on the updated ESMF) will cover pollution prevention and management measures especially for the Project financed public works. | Same timeframe as for the preparation and implementation of the ESMPs. | Ministry of Urban and Infrastructure/FPCU, Regions and participating cities. |
| ESS 4: COMMUNITY HEALTH AND SAFETY |  |  |  |
| 4.1 | TRAFFIC AND ROAD SAFETY Incorporate measures to manage traffic and road safety risks as required in the ESMP. | Same timeframe as for the preparation and implementation of the ESMP | Ministry of Urban and Infrastructure/FPCU, Regions and participating cities. |
| 4.2 | COMMUNITY HEALTH AND SAFETY Develop and implement measures and actions to assess and manage specific risks and impacts to the community arising from Project activities and include mitigation measures in the ESMPs to be prepared in accordance with the updated ESMF. | Same timeframe as for the preparation and implementation of the ESMP | Ministry of Urban and Infrastructure/FPCU, Regions and participating cities. |
| 4.3 | SEA AND SH RISKS Update and implement the SEA/SH Action Plan to assess and manage the risks of SEA and SH. | Update and implement the SEA/SH Action Plan throughout Project implementation | Ministry of Urban and Infrastructure/FPCU, MoLS, MoWSA, RRS, Regions and participating cities. |
| 4.4 | SECURITY MANAGEMENT Assess and implement measures to manage the security risks of the Project associated with the ESF, including the risks of engaging security personnel to safeguard project workers, sites, assets, and activities related to the preparation and implementation of the E&S risk management instruments. Update the Security Risk Assessment (SRA) and related Security Management Plan (SMP) that has been prepared for the parent project to minimize the risk of conflict and insecurity situation due to ESF-related activities. | Update and implement the SMP prepared for the parent Project throughout Project Implementation | Ministry of Urban and Infrastructure/FPCU, Regions and participating cities. |
| ESS 5: LAND ACQUISITION, RESTRICTIONS ON LAND USE AND INVOLUNTARY RESETTLEMENT |  |  |  |
| 5.1 | RESETTLEMENT FRAMEWORK and PLANS 1. Update and implement the Resettlement Policy Framework (RPF) that has been developed for the parent Project, consistent with ESS 5. 2. As required by the updated RPF and ESS5, prepare, adopt, and implement, and cause participating cities to prepare, adopt, and implement, resettlement plans (RAPs) for each subproject involving risks and impacts associated with land acquisition, involuntary resettlement (including physical and economic displacement) and land use restrictions, in accordance with ESS 5 and the updated RPF, and in a manner acceptable to the Association. - No displacement of people, and no loss of property during the implementation of the project - Vacant municipal and government land is being used for the implementation of subproject cleared from the third parties. | Update the RPF and implement throughout Project Implementation. Adopt and implement the respective RAP, including ensuring that before taking possession of the land and related assets, full compensation has been provided and as applicable displaced people have been resettled and moving allowances have been provided in advance of carrying out specific sub-activities under the Project. Implement RAPs fully throughout Project implementation including GRM to address resettlement and compensation related complaints | Ministry of Urban and Infrastructure/FPCU, Regions and participating cities. |
| ESS 6: BIODIVERSITY CONSERVATION AND SUSTAINABLE MANAGEMENT OF LIVING NATURAL RESOURCES |  |  |  |
| 6.1 | BIODIVERSITY RISKS AND IMPACTS Subprojects in and near ecologically sensitive areas, critical and natural habitats will not be financed, as defined in the subproject exclusion criteria included in the updated ESMF. The site-specific environmental and social risk management tools such as ESMPs will include biodiversity risk mitigation measures especially for the Project-financed public works involving urban greenery and plantation activities. | Same timeframe as for preparation of ESMPs under action 1.1 above, and implement throughout project implementation. | The Ministry of Urban and Infrastructure/FPCU; Regions and participating cities. |
| ESS 7: INDIGENOUS PEOPLES/SUB-SAHARAN AFRICAN HISTORICALLY UNDERSERVED TRADITIONAL LOCAL COMMUNITIES |  |  |  |
| 7.1 | This standard is not currently relevant. |  |  |
| ESS 8: CULTURAL HERITAGE |  |  |  |
| 8.1 | CULTURAL HERITAGE RISKS AND IMPACTS Adopt and implement measures to address potential risks to cultural heritage (tangible and intangible) in the updated ESMF and ESMP consistent with ESS8. | The ESMPs shall be prepared prior to commencement of public works. | The Ministry of Urban and Infrastructure, /FPCU, Regions, and participating cities. |
| 8.2 | CHANCE FINDS The updated ESMF includes a chance find procedure consistent with ESS8. The site-specific environmental and social risk management tools such as ESMPs, which will be prepared based on the updated ESMF, for public works such as small infrastructure, small-scale urban agriculture and watershed management activities will also include requirements for chance finds procedure. | No public works or activities shall be carried out until the relevant E&S instruments (e.g. ESMPs) are prepared, approved and disclosed for those works. These E&S instruments will be maintained and implemented throughout Project implementation | The Ministry of Urban and Infrastructure, /FPCU; Regions, participating cities |
| ESS 9: FINANCIAL INTERMEDIARIES |  |  |  |
| 9.1 | Not relevant for the project |  |  |
| ESS 10: STAKEHOLDER ENGAGEMENT AND INFORMATION DISCLOSURE |  |  |  |
| 10.1 | STAKEHOLDER ENGAGEMENT PLAN Update, adopt and implement a SEP for the Project, consistent with ESS10, which shall include measures to, inter alia, provide stakeholders with timely, relevant, understandable and accessible information, and consult with them in a culturally appropriate manner, which is free of manipulation, interference, coercion, discrimination and intimidation. | Updated SEP adopted for the Project prior to appraisal. Implement the SEP throughout Project implementation. | The Ministry of Urban and Infrastructure/FPCU; MoWSA, MoLS, and for RRS, Regions and participating cities. |
| 10.2 | PROJECT GRIEVANCE MECHANISM - All grievances shall be managed by the GRM for the Project, as described in the SEP, and in a manner acceptable to the Association. - Ensure and cause participating cities to ensure implementation, monitoring, and reporting on the GRM. The grievance mechanism shall be equipped to receive, register, and facilitate the resolution of SEA/SH complaints, including through the referral of survivors to relevant gender-based violence service providers, all in a safe, confidential, and survivor-centered manner. | - RGM operationalized prior to selection of beneficiaries at the city level and to be implemented throughout Project period. - Throughout Project implementation, with detailed information included in the reports set out in Section A of this ESCP. | The Ministry of Urban and Infrastructure, /FPCU; MoWSA, MoLS, and RRS, Regions and participating cities. |
| INDICATORS FOR IMPLEMENTATION READINESS |  |  |  |
| The second Additional Financing for the Project is in the implementation phase in existing cities. Systems are in place, E&S staffing arrangements are in place for federal level coordination offices and regional states, except Central Ethiopia region; E&S focal persons are assigned and working in all the Project implementation cities. Also, the SEP has been updated for the third Additional Financing. |  |  |  |